## Sheet1
WEEK 1 ( FEB 27 - MARCH 5)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Discussiong about Task allocation | Decide on ways to track the progress, scrum board | None
Ravindar Reddy | Find details and information about Backend tech Stack | Decide the tables required | None
Preethi Billa | Discusson about Sprint Tenure | Decide on cloud deployment | None
Mounica Reddy | Discuss the Frontend tech Stack | Decide the total Pages required for the work | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect
WEEK 2 ( MARCH 6 - MARCH 12)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Was the scrum master for this sprint. Meanwhile also worked on the frontend decisions along with the tables | Dsign frontent booking route component | None
Ravindar Reddy | Finalized the table structure for the Database | Dockerizing the Backend/start creation of API's | None
Preethi Billa | Decided to proceed with AWS. | Learning Tech stack( React, Spring, MongoDB) | None
Mounica Reddy | Decided the total Pages required for the work | Learning Tech stack( React, Spring, MongoDB) | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect
WEEK 3 ( MARCH 13 - MARCH 19)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Completion booking route | Design Home Page component | None
Ravindar Reddy | Completed Dockerizing the Backend and started creating RestAPI's | Continue to work on Backend Rest API's(create and update) | None
Preethi Billa | Got acquainted with tech stack | Plan how to deploy on cloud | None
Mounica Reddy | Got acquainted with tech stack and pushed a sample homepage | Decide the routing of pages and give a basic information about the looks of the page | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect
WEEK 4 ( MARCH 20 - MARCH 26)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Working on completing the home page | Add nav, header, footer bar to the home page | Waiting for the relevant data
Ravindar Reddy | Completed Backend Rest API's(create and update) | Creation of login and signup with JWT | None
Preethi Billa | Planned how to deploy on cloud | Create testing document | None
Mounica Reddy | Decided the routing of pages and the basic information about the look of the pages | Create dummy data in JSON format | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect
WEEK 5 ( MARCH 27 - APRIL 2)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Completed home page | Create login and sign up and banner page | None
Ravindar Reddy | Continue to work on login and signup with JWT | Complete login and signup with JWT | None
Preethi Billa | Testing document done | Create payment confirmation page | None
Mounica Reddy | Created dummy data in JSON format | Create room overview page | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect
WEEK 6 ( APRIL 3 - APRIL 9)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Completed login, sign up and banner | Create a search and update page, integrated with backend using auth.js file | None
Ravindar Reddy | Completed login and signup with JWT | work on dynamic pricing logic, delete booking, reward points logic | None
Preethi Billa | Created payment confirmation page | Create purchase history page | None
Mounica Reddy | Created room overview page | Create an employee page to view hotel booking history | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect
WEEK 7 ( APRIL 10 - APRIL 16)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Created a search and update page, integrated with backend using auth.js file | Validate integration with backend for few completed pages, create a rewards page | None
Ravindar Reddy | completed dynamic pricing logic. | continue to work on Delete booking, Reward points logic, Field validations | None
Preethi Billa | Created purchase history page | Modify purchase history page | None
Mounica Reddy | Created an employee page to view hotel booking history | CSS for the purchase history | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect
WEEK 8 ( APRIL 17 - APRIL 23)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Validate integration with backend for few completed pages, create a rewards page | Validate integration with backend and modification to pages | None
Ravindar Reddy | completed Delete booking, Reward points logic, Field validations | Validate integration with frontend for few completed pages | None
Preethi Billa | Modified purchase history page | UI wireframes | None
Mounica Reddy | CSS for the purchase history done | Create class diagram and architecture diagram | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect
WEEK 9 ( APRIL 24 - APRIL 30)
Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Shreyansh Upadhyay | Validate integration with backend and modification to pages | Backend deployment on cloud | None
Ravindar Reddy | Validate integration with frontend and modification to api's | Backend deployment on cloud | None
Preethi Billa | UI wireframes | Frontend deployment on cloud | None
Mounica Reddy | Create class diagram and architecture diagram | Frontend deployment on cloud | None
Scrum Master = Shreyansh Upadhyay
XP Core Value
1. Feedback
2. Comunication
3. Respect