## Sheet1
Sprint 1
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Decide the frontend designs and Task allocation | Decide on ways to track the progress, scrum board | Shreyansh | 8 | 2022-03-01: 2; 2022-03-03: 1; 2022-03-05: 1; 2022-03-08: 1; 2022-03-10: 2; 2022-03-12: 1
Backend Technology Search | Deciding on backend Technology ,design and architecture | Ravindar | 8 | 2022-02-27: 2; 2022-02-28: 1; 2022-03-03: 2; 2022-03-06: 1; 2022-03-07: 1; 2022-03-09: 1
Front End Technology Search | Deciding on front end technology | Mounica | 8 | 2022-03-01: 2; 2022-03-02: 1; 2022-03-03: 1; 2022-03-05: 1; 2022-03-07: 2; 2022-03-08: 1
Sprint Details | What all details are required to be documented | Preethi | 8 | 2022-03-04: 2; 2022-03-05: 1; 2022-03-07: 2; 2022-03-08: 1; 2022-03-10: 1; 2022-03-11: 1
Remaining Effort |  |  | 32 | 30 | 29 | 25 | 24 | 20 | 18 | 15 | 14 | 9 | 6 | 5 | 2 | 1 | 0
Ideal Trend |  |  | 32 | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16 | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | 0
Sprint 2
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Design the routing flow for the users, Landing/Homepage for the user | Create the flow of the website and the Homepage for the user | Shreyansh | 14 | 2022-03-13: 2; 2022-03-15: 3; 2022-03-18: 3; 2022-03-20: 2; 2022-03-21: 1; 2022-03-22: 1; 2022-03-26: 2
Dockerizing and integration technologies | Dockerizing the Backend/start creation of API's and Explore ways to integrate backend and frontend. | Ravindar | 14 | 2022-03-14: 3; 2022-03-15: 4; 2022-03-16: 1; 2022-03-17: 2; 2022-03-21: 2; 2022-03-26: 2
Pushed a sample home page | Decide the routing of pages and give a basic information about the display of pages | Mounica | 11 | 2022-03-14: 2; 2022-03-15: 3; 2022-03-18: 1; 2022-03-21: 1; 2022-03-22: 1; 2022-03-23: 1; 2022-03-24: 2
Planned how to deploy on cloud | Create testing document | Preethi | 10 | 2022-03-14: 1; 2022-03-15: 2; 2022-03-16: 2; 2022-03-19: 2; 2022-03-21: 1; 2022-03-24: 2
Remaining Effort |  |  | 49 | 47 | 41 | 29 | 26 | 24 | 20 | 18 | 16 | 11 | 9 | 8 | 4 | 4 | 0
Ideal Trend |  |  | 49 | 45.5 | 42 | 38.5 | 35 | 31.5 | 28 | 24.5 | 21 | 17.5 | 14 | 10.5 | 7 | 3.5 | 0
Sprint 3
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Add SearchPage, NavigationPage and CustomerDetails Page and Integrate with Backend | Create SearchPage, NavigatioPage and connect with backend using axios | Shreyansh | 14 | 2022-03-27: 1; 2022-03-28: 1; 2022-03-29: 2; 2022-03-31: 1; 2022-04-01: 3; 2022-04-03: 3; 2022-04-05: 1; 2022-04-08: 1
Backend Rest API's creation | create ,update and login and signup with JWT token | Ravindar | 14 | 2022-03-27: 2; 2022-03-29: 3; 2022-03-30: 3; 2022-04-02: 2; 2022-04-03: 1; 2022-04-05: 1; 2022-04-07: 1; 2022-04-09: 2
Created dummy data in JSON format and create room overview page | Create an employee page to view hotel booking history | Mounica | 14 | 2022-03-28: 3; 2022-03-30: 3; 2022-04-01: 1; 2022-04-03: 2; 2022-04-06: 1; 2022-04-07: 2; 2022-04-08: 2
Create payment confirmation page | Create purchase history page | Preethi | 14 | 2022-03-27: 2; 2022-03-28: 1; 2022-03-30: 2; 2022-03-31: 3; 2022-04-03: 1; 2022-04-05: 2; 2022-04-06: 1; 2022-04-08: 2
Remaining Effort |  |  | 56 | 51 | 46 | 41 | 33 | 29 | 25 | 23 | 16 | 16 | 12 | 10 | 7 | 2 | 0
Ideal Trend |  |  | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Sprint 4
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Integration of Frontend with Backend and Creating a Rewards Page | Integrate the React app with backend,and show the user his rewards points | Shreyansh | 14 | 2 | 1 |  | 2 | 3 |  |  | 1 | 1 | 1 | 1 |  | 1 | 1
dynamic pricing and rewards logic | work on dynamic pricing logic, delete booking, reward points logic | Ravindar | 14 | 2022-04-10: 3; 2022-04-12: 3; 2022-04-13: 2; 2022-04-16: 1; 2022-04-17: 2; 2022-04-19: 2; 2022-04-21: 1
CSS for the purchase history | Create a component diagram and architecture diagram | Mounica | 10 | 2022-04-11: 3; 2022-04-13: 3; 2022-04-15: 1; 2022-04-17: 2; 2022-04-20: 1
Modify purchase history page | UI wireframes | Preethi | 9 | 2022-04-11: 1; 2022-04-13: 1; 2022-04-14: 3; 2022-04-17: 2; 2022-04-19: 2
Remaining Effort |  |  | 47 | 42 | 37 | 34 | 26 | 20 | 19 | 18 | 11 | 10 | 5 | 3 | 2 | 1 | 0
Ideal Trend |  |  | 47 | 43.6429 | 40.2857 | 36.9286 | 33.5714 | 30.2143 | 26.8571 | 23.5 | 20.1429 | 16.7857 | 13.4286 | 10.0714 | 6.7143 | 3.3571 | 0
Sprint 5
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19
Deployment of the App on AWS | Deploy the frontend on AWS EC2, and work on Documentation | Shreyansh | 16 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 |  |  |  |  | 1 | 1 | 1 | 1 |  | 1
Deployment on cloud | Deployed the applicaiton on AWS cloud and checked the complete working of the application and worked on documentation | Ravindar | 15 | 2022-04-24: 3; 2022-04-26: 3; 2022-04-30: 1; 2022-05-01: 2; 2022-05-03: 2; 2022-05-05: 1; 2022-05-08: 1; 2022-05-09: 1; 2022-05-10: 0; 2022-05-12: 1
Frontend deployment on cloud | Creating usecase diagram and working on the documentation | Mounica | 15 | 2022-04-25: 1; 2022-04-27: 2; 2022-04-29: 3; 2022-05-01: 1; 2022-05-04: 2; 2022-05-05: 2; 2022-05-07: 1; 2022-05-08: 1; 2022-05-09: 1; 2022-05-10: 0; 2022-05-12: 1
Deployment on cloud | Working on the documentation | Preethi | 15 | 2022-04-25: 1; 2022-04-26: 1; 2022-04-27: 1; 2022-04-28: 3; 2022-04-30: 1; 2022-05-01: 2; 2022-05-03: 2; 2022-05-05: 2; 2022-05-06: 1; 2022-05-08: 1
Remaining Effort |  |  | 61 | 57 | 54 | 49 | 45 | 41 | 37 | 34 | 27 | 25 | 21 | 19 | 14 | 13 | 11 | 7 | 4 | 3 | 3 | 0
Ideal Trend |  |  | 61 | 57.7895 | 54.5789 | 51.3684 | 48.1579 | 44.9474 | 41.7368 | 38.5263 | 35.3158 | 32.1053 | 28.8947 | 25.6842 | 22.4737 | 19.2632 | 16.0526 | 12.8421 | 9.6316 | 6.4211 | 3.2105 | 0